## Slide 1
Presented by :
Dr. Mukul Shastry
Yogita Potaliya
LEGAL CHALLENGES IN HIGHWAY PROJECTS: THE ROLE OF ARBITRATION

## Slide 2
Introduction
Importance of Highway Infrastructure and PPPs:
Highway infrastructure is vital for economic growth, facilitating trade, connectivity, and regional development.
It enhances mobility, reduces transportation costs, and supports the movement of goods and people across regions.
Role of Public-Private Partnerships (PPPs):
PPPs enable the leveraging of private sector efficiency and investment in public infrastructure projects.
They bring in innovation, risk-sharing, and additional funding sources, accelerating project implementation.
Common Legal and Operational Issues:
Land Acquisition: Delays due to legal disputes, compensation issues, and resistance from landowners can stall projects. Such delays often lead to cost overruns and strained relationships between stakeholders.
Scope Changes and Construction Delays: Arising from design changes, inadequate utility mapping, and unforeseen site conditions, these factors contribute to extended project timelines and increased financial burden.
Toll Revenue Challenges: Discrepancies in traffic projections, policy changes affecting toll collection, and public opposition, lack of anticipated support. This impacts return on investment and jeopardizes financial viability.
Arbitration as a Dispute Resolution Mechanism:
Preferred for its efficiency, confidentiality, and expertise in handling complex infrastructure disputes.
Arbitration allows for tailored solutions and reduces the burden on traditional courts.
Department of Expenditure Guidelines (2024): Arbitration clauses in government contracts are recommended only for disputes valued below ₹10 crore.
Under these guidelines, for higher-value disputes, inclusion of arbitration clauses requires approval from senior authorities.

## Slide 3
Common Disputes in Highway Projects
Construction Disputes:
Delay in Land Handover: Authorities often face challenges in timely land acquisition, impacting project timelines.
This leads to idle resources and escalated project costs, both direct as well indirect due to project prolongation.
Cost Overruns: Due to design modifications, unexpected utility relocations, and inflation.
Such overruns strain budgets and grounds for renegotiation of contracts is limited.
Quality Disputes: Concerns over construction standards, leading to disputes during the defects liability period.
Application of bid discount over changed scope.
Toll Disputes:
Traffic Projections vs. Actual Usage: Disparities leading to revenue shortfalls and financial stress.
Accurate forecasting is essential for financial planning and investor confidence.
Toll Rate Revisions: Delay in approval affects revenue models directly and affects projected set-off towards inflation.
Free Passage Policies: Exemptions beyond NH Fee Rules also reduce toll income and related compensation is limited.
External Events: Demonetization, pandemics, and shifts to digital tolling disrupt revenue streams and relief is uncertain.
Such events require adaptive strategies to mitigate financial impacts.

## Slide 4
Dispute Resolution Tools under Concession Agreements
Available Methods:
Negotiation: Initial step to amicably resolve disputes. It encourages open communication and mutual understanding.
Dispute Resolution Boards (DRBs): Panels providing non-binding recommendations. They offer expert insights to preempt escalation of disputes.
Arbitration: Binding resolution by neutral arbitrators. It ensures confidentiality and specialized adjudication.
Mediation: A voluntary and confidential process where a neutral third party, the mediator, facilitates communication between disputing parties to help them reach a mutually acceptable agreement.
Conciliation: Voluntary and confidential alternative dispute resolution process where a neutral third party, the conciliator, assists disputing parties in reaching a mutually acceptable agreement. Unlike mediation, the conciliator may propose non-binding settlement options to facilitate resolution. CCIE (NHAI) would fall under this ADR tool.
Litigation: Court proceedings as a last resort. Often time-consuming and public, impacting project timelines.
Arbitration's Significance:
Offers a specialized forum with expertise in infrastructure disputes.
Facilitates faster resolution compared to traditional litigation.

## Slide 5
Arbitration and Conciliation Act, 1996 – Legal Framework
The Act provides a comprehensive legal framework for conducting arbitration and conciliation in India, based on UNCITRAL Model Law
Positive Aspects:
Time-Bound Process: Section 29A mandates arbitration awards within 12-18 months.
Institutional Arbitration: Post-2019 amendments promote the use of arbitral institutions for appointing arbitrators.
Limited Grounds for Challenge: Section 34 narrows the scope for setting aside awards, enhancing finality.
Challenges:
Enforcement Delays: Court interventions can stall the execution of arbitral awards.
Bias in Arbitrator Appointments: Concerns arise when government entities are involved in appointing arbitrators.
Ambiguity in 'Public Policy': Vague definitions allow for broad interpretations, leading to challenges against awards.
Lack of Specialized Institutions: Need for sector-specific arbitral bodies to handle complex infrastructure disputes.

## Slide 6
Arbitration - Efficacious measures recommended
Express provision for Arbitration: to be mentioned within the Agreement
Seat of arbitration and whether institutional: Provision to define agreement over the seat of arbitration, including if the institutional arbitration is desired then the same can be provided for.
Non-Payment of Arbitral Awards: Delays or refusals in honoring awards strain financial resources of operators. This affects cash flows and project sustainability.
Disclosure from Arbitrators and reliance of IBA guidelines to avoid conflict of interest: to ensure impartiality and independence of arbitrators. Updated in 2024 to address modern concerns such as third-party funding, social media presence, and organizational structures of law firms.
IBA Rules on the Taking of Evidence in International Arbitration (2020): Offer procedures for the efficient and fair taking of evidence, aspects like document production, witness testimony, expert reports, and inspections.
IBA guidelines on virtual hearing: There is deliberation on virtual hearings and guidelines on admissibility of illegally obtained evidence has also been provided.

## Slide 7
NHAI Initiatives
Objective: Introduced by NHAI in 2017 to facilitate amicable settlement of disputes in highway projects and reduce reliance on arbitration and litigation.
Revised SOP (2025) allows individual disputes to be addressed separately for enhanced flexibility.
CCIE Process and Procedures:
Disputes are referred to the CCIE by contractors, concessionaires, or consultants.
NHAI allocates an expert panel (comprising of retired High Court Judges, senior public administrators, and domain experts).
CCIE recommendations are binding if accepted by both parties.
Efficient process to conclude within a maximum of 6 months.
Conciliation meetings by the Panel to facilitate settlement.
If settlement is reached, a final report is submitted; otherwise, unresolved disputes may proceed to arbitration.
Conciliation Committee of Independent Experts (CCIE)
As of April 2022, the Conciliation Committees of Independent Experts (CCIE), established by the National Highways Authority of India (NHAI), have successfully resolved 155 infrastructure dispute cases. These cases involved total claims amounting to approximately ₹38,747 cr., with settlements reached for about ₹13,067 cr.
(source: https://www.financialexpress.com/business/roadways-nhai-settles-60-conciliation-cases-in-fy22-2483936/?utm_source=chatgpt.com)

## Slide 8
Resolution under Arbitration and CCIE Committee
Comparison of
Arbitration
vs.
CCIE Committee
Aspect | Arbitration | CCIE Committee
Nature | Adjudicatory | Conciliatory
Binding Decision | Yes, subject to limited appeals | Only if parties agree to settlement
Timeframe | Longer, depends on complexity | Generally quicker
Cost | Higher due to fees and legal expenses | Lower, minimal administrative costs, no law/advocate fee involved
Confidentiality | Maintained | Maintained
Enforceability | Enforceable as court decree | Enforceable upon agreement
Grounds for Challenge | Limited grounds as per Section 34 of the Arbitration and Conciliation Act, 1996 | Not applicable, as the outcome is a settlement agreement reached by consensus.

## Slide 9
Arbitration - Efficacious Measures Recommended
Express provision for Arbitration: to be mentioned within the Agreement
Seat of arbitration and whether institutional: Provision to define agreement over the seat of arbitration, including if the institutional arbitration is desired then the same can be provided for.
Non-Payment of Arbitral Awards: Delays or refusals in honoring awards strain financial resources of operators. This affects cash flows and project sustainability.
Disclosure from Arbitrators and reliance of IBA guidelines to avoid conflict of interest: to ensure impartiality and independence of arbitrators. Updated in 2024 to address modern concerns such as third-party funding, social media presence, and organizational structures of law firms.
IBA Rules on the Taking of Evidence in International Arbitration (2020): Offer procedures for the efficient and fair taking of evidence, aspects like document production, witness testimony, expert reports, and inspections.
IBA guidelines on virtual hearing: There is deliberation on virtual hearings and guidelines on admissibility of illegally obtained evidence has also been provided.

## Slide 10
Adverse Orders under Section 34 & 37
Section 34 – Setting Aside Arbitral Awards
Allows challenge on limited grounds:
Incapacity of party or invalid arbitration agreement.
Procedural unfairness (e.g., no notice, denied hearing).
Exceeds scope of submission to arbitration / non-arbitrable subject matter.
Public policy violation – fraud, corruption, contrary to fundamental policy, morality, or justice.
Note: The scope of “public policy” was narrowed by the Arbitration and Conciliation (Amendment) Act, 2015, effective from October 23, 2015. As held in Ssangyong Engineering v. NHAI, (2019), the amendment is prospective in nature.
Section 37 – Appeals Against Orders
Provides for appeals against specific orders under the Act, including:
Setting aside/refusing to set aside award under Section 34.
Accepting/rejecting jurisdictional objections under Section 16.
Granting/refusing interim measures under Section 17.
In exercising appellate jurisdiction under Section 37, courts are not meant to reappreciate evidence or interpret the contract, except in cases where the award is patently illegal or shocks the judicial conscience (MMTC Ltd. v. Vedanta Ltd., 2019).
Under Section 34 as well as Section 37, courts do not have the power to modify the arbitral award; they may only set it aside or remit the matter back to the tribunal for reconsideration (NHAI v. M. Hakeem, 2021).

## Slide 11
MORTH Initiatives applicable for NHAI
Launched first time in May 2023, MORTH issued Office Memorandum to implement one time settlement scheme called Vivad se vishwas to effectively settle pending disputes on the arbitral awards and court orders.
The scheme encourages amicable settlements by way of conciliation mechanism under the Arbitration and Conciliation Act ,1996, to provide quick dispute closure and improve liquidity.
Process involves claim submission, committee review, settlement proposal, and legal closure upon acceptance.
This scheme provides for a one-time settlement under which the dispute can be settled by paying a certain percentage of the disputed amount.
The deadline for applying for settlement under this scheme is being extended from time to time to by the Authority and the last extension was till 31st March 2024 for awards till 31st Jan 2023 and Court Orders issued till 30th April 2023.
"Vivad se Vishwas" Scheme
Under this scheme NHAI and PNC Kanpur Highways Limited dispute was resolved.
On May 9, 2024, PNC Infratech paid Rs 391 crore under the 'Vivaad se Vishwas II (Contractual Disputes)' scheme of the Government of India, which was a landmark settlement agreement.

## Slide 12
Legal Aspects
Specific legal challenges faced by the
Highway operators
Solutions and best practices

## Slide 13
Specific Legal Challenges Faced by Highway Operators
Land Acquisition Disputes:
  LARR Act, 2013 - Delays in securing land, disputes over compensation, and resistance from landowners often stall projects.
  Case in point: Delhi-Amritsar-Katra Expressway. Forceful repossession of land by landowners in Sangrur, Malerkotla, and Fazilka districts of Punjab. INR 40,000 crore project got scuttled.
Toll Policy and Revenue Collection Issues:
  Operators allege that NHAI or government policies (e.g., toll exemptions during protests or for specific vehicles) erode revenue, breaching concession agreements.
  DND Flyway case – Allahabad HC ruled against perpetual tolling. (no defined date and 20%. ROI deemed illegal)

## Slide 14
Specific Legal Challenges Faced by Highway Operators
Contractual Breaches and Termination Disputes
  Concession agreements with NHAI often lead to disputes over scope changes, delays in approvals (e.g., General Arrangement Drawing by Railways), or premature termination due to defaults by either party.
Road Safety and Liability for Accidents
  Highway operators face legal exposure for accidents due to poor maintenance, inadequate signage, or design flaws. National Highways account for 36% of India’s 171,000 road fatalities (2022), despite being 2% of the road network.
Regulatory and Policy Instability
  Inconsistent highway development policies and lack of coordination among agencies (e.g., NHAI, state governments, RTOs) create uncertainty. Overloading, legalized by some states via special tokens, violates the Motor Vehicles Act and damages roads. Enforcement is weak any which way.
  Environmental clearances (rules change as per State)/LARR requires social impact assessment.

## Slide 15
Solutions and Best Practices
Legal & Contractual Measures:
  Fast Track Arbitration: Mandatory 12-18 months period. For Sec.34/37 also mandate timeline for courts else deemed dismissal of application.
  Specialized Arbitration Benches in Courts – Dedicated to hear Sec. 34/37 only.
  Modern age Arbitrators: Have people from industry as arbitrators and not merely the retired judges.
  Mediation First: Promote pre-arbitration mediation under the Commercial Courts Act, 2015, to settle disputes amicably, avoiding costly Section 34/37 litigation.
  Award Transparency: Require arbitral tribunals to publish reasoned awards, aligning with Ssangyong (2019), to reduce Section 34 challenges for procedural unfairness.
Policy Reforms:
  Transparent Compensation Mechanisms: Implement market-based compensation aligned with the LARR Act. Conduct independent audits of land valuations to ensure fairness, reducing disputes like those in Punjab where farmers demanded Rs 1.5 crore per acre against NHAI’s Rs 25 lakh.
  Pre-Project Community Engagement.
  Dedicated Land Acquisition Tribunals: Establish fast-track tribunals to resolve compensation disputes, reducing court backlogs.
  Digital Land Records: Use blockchain-based land registries to verify ownership and prevent disputes, ensuring encumbrance-free land handover.
Toll Related issues may be addressed:
  Fixed Concession Period / Dynamic Toll Adjustment/ Revenue Sharing Models/Public Awareness Campaigns.

## Slide 16
Solutions and Best Practices
Mitigating Road Safety Liabilities:
  Mandatory Safety Audits: Conduct regular third-party safety audits to ensure compliance with Indian Road Congress (IRC) standards, addressing issues like poor signage or geometric designs.
  Clear Indemnity Clauses: Include clauses in contracts shifting design-related liabilities to NHAI or consultants, reducing operator exposure.
  Technology Integration: Deploy AI-based traffic monitoring and IoT sensors for real-time maintenance alerts, improving safety and deflecting tort claims under the Motor Vehicles Act, 1988.
  Insurance Mechanisms: Mandate comprehensive liability insurance for operators to cover accident claims, reducing financial risks and arbitration over indemnities.
Environment and Social Issues:
  Proactive Clearances: Obtain environmental clearances under the Environment Protection Act, 1986, before bidding, using GIS-based impact assessments to pre-empt PILs.
  Social Impact Mitigation: Implement robust rehabilitation plans under the LARR Act, offering skill training or alternative livelihoods to affected communities, reducing resistance like Punjab’s farmer protests.

## Slide 17
CASE LAWS
Delhi Gurgaon Expressway
Reliance Infra (TKTR) v. NHAI
DMRC v. DAMEPL
Afcon Infra v. Ircon
Gayatri Balasamy v. NHAI

## Slide 18
Project Overview
  27.7 km, 6/8-lane BOT project, commissioned 2008
  Concessionaire: Delhi Gurgaon Super Connectivity Ltd. (DGSCL)
  20-year concession, negative grant (Rs 61 crore to NHAI)
Arbitration Trigger (2011–2012)
  NHAI termination notices for:
    Congestion failures
    No maintenance plan
    Unauthorized refinancing
  Lenders (IDFC) contested, citing Rs 1,400 crore exposure
  Section 9 plea DGSCL sought toll collection rights at Rajokari
Key Disputes
  Validity of termination notices
  Toll plaza operations (11% service charge for MCD tax)
  Lender rights amid unapproved refinancing
Judicial Pronouncement: In 2014, the Delhi High Court accepted a settlement where IDFC took over the project, dismantled the Sirhol toll plaza (km 24), and shifted tolling to Kherki Dhaula (km 42), ending arbitration disputes. The court directed IDFC to appoint a new concessionaire within 90 days, resolving claims against DGSCL and NHAI.
Delhi-Gurgaon Expressway Arbitration Case

## Slide 19
Reliance Infra v. NHAI
Background
TK Toll Road Pvt. Ltd. (TKTR), a wholly-owned subsidiary of Reliance Infrastructure Limited (RInfra), operated an 82 km, 4-lane stretch of NH-67 under a 2006 BOT concession agreement with NHAI.
Arbitral Award (October 2022):
A three-member arbitral tribunal unanimously awarded TKTR Rs 1,200 crore (including interest) for:
NHAI’s Section 34 Challenge:
NHAI petitioned the Delhi High Court to set aside the award, arguing:
Disputes arose due to NHAI’s delays in providing encumbrance-free land, causing cost overruns, and a toll plaza relocation that reduced revenue. Arbitration was initiated in 2018, following a 2013 supplementary agreement waiving certain delay-related claims.
The claims were time-barred under the Limitation Act, 1963.
The award was based on “conjectures and assumptions” (e.g., revenue loss calculations).
It violated public policy under Section 34(2)(b)(ii), invoking post-2015 grounds (fraud or corruption)
The tribunal lacked jurisdiction due to the 2013 supplementary agreement waiving claims.
Cost overruns due to land acquisition delays.
Revenue losses from toll plaza relocation, calculated as a percentage of revenue until the concession’s end (January 14, 2038).
The award’s net present value included Rs 50 crore for future revenue losses.

## Slide 20
Reliance Infra v. NHAI - Delhi High Court Ruling (August 9, 2023)
Dismissal of Challenge:
The court, presided by Justice Navin Chawla, dismissed NHAI’s petition, upholding the arbitral award.
Key Findings:
    No Patent Illegality: The tribunal’s findings were based on evidence, not conjectures, and aligned with the arbitral record, per Ssangyong Engineering v. NHAI (2019), which restricts Section 34 interference to clear errors.
    Public Policy: NHAI failed to prove fraud, corruption, or violation of India’s fundamental policy, as required post-2015 amendment. The award was consistent with public interest, compensating TKTR for NHAI’s breaches.
    Jurisdiction and Limitation: The 2013 agreement did not bar claims for ongoing losses (e.g., toll plaza relocation), and the tribunal had authority to adjudicate. Claims were within the limitation period, as losses persisted post-2013.

## Slide 21
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Project Overview
The Delhi Airport Metro Express Line, a 22.7 km metro connecting New Delhi Railway Station to Indira Gandhi International Airport, was developed under a 2008 Concession Agreement between Delhi Metro Rail Corporation (DMRC), a state-owned entity, and Delhi Airport Metro Express Pvt. Ltd. (DAMEPL), a special-purpose vehicle formed by a consortium of Reliance Infrastructure Ltd. (RInfra) and Construcciones y Auxiliar de Ferrocarriles SA, Spain.
DMRC was responsible for civil works and government clearances, while DAMEPL handled financing, design, installation, and operations. The concession period extended until August 2038.
The project faced delays, with commercial operations starting in February 2011 after safety clearances from the Commissioner of Metro Railway Safety (CMRS).

## Slide 22
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Dispute Origin
In 2012, DAMEPL identified structural defects (e.g., cracks in girders) in DMRC’s civil works, alleging safety risks. On July 8, 2012, DAMEPL halted operations, citing unsafe conditions, and issued a notice to DMRC to cure defects within 90 days.
On October 8, 2012, DAMEPL issued a termination notice, claiming DMRC failed to cure defects, constituting a material breach under Clause 29.5.1(i) of the agreement, which allowed termination if DMRC “failed to cure such breach or take effective steps for curing such breach” within the cure period.
DMRC disputed the termination and initiated arbitration. Meanwhile, both parties jointly applied to CMRS for line reopening. On January 18, 2013, CMRS issued a conditional sanction with speed restrictions (50 kmph, increasable to 80 kmph in 10 kmph steps), allowing operations to resume.
DAMEPL resumed operations in January 2013 but handed over the line to DMRC on June 30, 2013, citing persistent issues. DMRC has operated the line since July 2013.

## Slide 23
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Arbitration Proceedings
Arbitral Tribunal (May 11, 2017): A three-member tribunal ruled in favor of DAMEPL, awarding Rs 2,782.33 crore plus interest (totaling ~Rs 7,687 crore by 2024), finding:
    DMRC’s failure to fully cure defects (e.g., girder cracks) within the 90-day cure period validated DAMEPL’s termination notice.
    The CMRS certificate’s speed restrictions (50 kmph) indicated unresolved defects, undermining the project’s high-speed connectivity goal.
DMRC’s subsequent operation of the line was irrelevant to the termination’s validity: The tribunal interpreted Clause 29.5.1(i) to require full defect correction, not merely “effective steps”.
Key Issue: Whether DMRC’s actions constituted “effective steps” to cure defects, rendering the termination invalid.

## Slide 24
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Judicial Journey
Delhi High Court (Single Judge, 2018): DMRC challenged the award under Section 34, alleging patent illegality and public policy violations. The Single Judge dismissed the petition, upholding the tribunal’s findings as evidence-based and plausible, per Associate Builders v. DDA (2015). The judge noted the CMRS certificate’s conditions showed incomplete repairs, failing the high-speed connectivity objective.
Delhi High Court (Division Bench, January 15, 2019): DMRC appealed under Section 37. The Division Bench partly allowed the appeal, setting aside the award, finding:
    The tribunal ignored vital evidence, notably the CMRS certificate, which indicated “effective steps” were taken, as operations resumed under statutory safety compliance (Metro Railways Act, 2002).
    The award was perverse and patently illegal under Section 34(2A), as it misread the termination clause and overlooked DMRC’s incremental progress.
    Issues not decided were remanded for fresh arbitration.

## Slide 25
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Supreme Court (September 9, 2021)
DAMEPL filed a Special Leave Petition (SLP) under Article 136.
A two-judge bench reversed the Division Bench, restoring the arbitral award, holding:
The Division Bench overstepped Section 34’s narrow scope by re-evaluating facts and substituting its view, violating Ssangyong Engineering v. NHAI (2019).
The tribunal’s findings on defects and CMRS conditions were factual, not open to judicial review unless patently unreasonable.
Patent illegality requires errors “going to the root of the matter,” not superficial misinterpretations.
Review Petition (November 2021):
DMRC’s review petition was dismissed, affirming the 2021 judgment.

## Slide 26
Delhi Metro Rail Corporation v. Delhi Airport Metro Express Pvt. Ltd.
Curative Petition (April 10, 2024): DMRC filed a curative petition under Article 142, an extraordinary remedy for “grave miscarriage of justice” or “abuse of process”. A three-judge bench (CJI D.Y. Chandrachud, Justices B.R. Gavai, Surya Kant) allowed the petition, setting aside the 2021 judgment and arbitral award, restoring the Division Bench’s 2019 ruling.
Key findings:
Patent Illegality: The tribunal misinterpreted Clause 29.5.1(i), that allowed termination only if DMRC failed to cure defects or take “effective steps.”
The CMRS certificate, issued after joint application and inspection, showed DMRC took effective steps (e.g., repairs enabling safe operations at 50 kmph), invalidating the termination.
Ignoring Vital Evidence: The tribunal wrongly focused on CMRS speed restrictions, concluding defects were uncured, and failed to explain why DMRC’s actions weren’t “effective steps.” This rendered the award perverse, per Associate Builders (2015) and Ssangyong (2019).
Miscarriage of Justice: The 2021 Supreme Court judgment, by restoring the award, caused a “grave miscarriage of justice” by imposing a Rs 7,687 crore burden on a public utility, despite evidence of DMRC’s compliance. The Division Bench correctly identified the award’s illegality.
Curative Scope: The court clarified curative jurisdiction is exceptional, not a routine fifth stage of challenge, but justified here to prevent public fund misuse.
Outcome: The award was set aside, relieving DMRC of the liability. DAMEPL’s Rs 2,802 crore investment was noted, but DMRC had paid Rs 2,599.18 crore, with Rs 5,088 crore outstanding as of January 31, 2024.

## Slide 27
Afcons Infra v. Ircon
Project: USBRL rail project in J&K, executed by Ircon; Afcons subcontracted for tunnels and bridges (contract dated Nov 4, 2004).
Dispute: Delays blamed on both sides – Afcons for inefficiency, Ircon for delayed site access and approvals. Afcons sought EOT and costs; Ircon imposed penalties.
Arbitration: Tribunal upheld Afcons' claims, granted EOT and compensation; rejected Ircon’s counterclaims.
Ircon’s Challenge (Sec 34):
  Grounds: Patent illegality, violation of natural justice, public policy breach.
  Court Ruling (Delhi HC, Apr 26, 2023): Challenge dismissed.
Key Findings:
  EOT award based on evidence and contract – no patent illegality.
  Natural justice upheld – fair hearings and due process followed.
  No public policy violation – award enforceable.
Significance: Reinforces finality of arbitration in infra disputes; limited judicial interference under Sec 34 & 37.

## Slide 28
Gayatri Balasamy v. ISG Novasoft (2025)
Bench Composition: 5-Judge Constitution Bench
  Majority Decision: 4:1
  Majority Opinion (Authored by CJI Sanjiv Khanna)
Limited Modification Power:
  Courts can modify arbitral awards under Section 34 in narrowly defined circumstances, resolving the conflict with M. Hakeem (2021), which barred modifications.
Permissible modifications include:
  Severable Awards: When an invalid part (e.g., on a non-arbitrable issue) can be surgically separated without affecting the valid portion (e.g., severing unrelated damages, as in J.C. Budhraja v. Orissa Mining, 2008).
  Clerical Errors: Correcting computational, typographical, or clerical mistakes, per Section 34(2)(b)(i).
  Post-Award Interest: Adjusting interest rates or periods, as in Tata Hydroelectric v. Union of India (2003).
  Article 142: Exceptional modifications to achieve “complete justice,” exercised cautiously (e.g., Oriental Structural Engineers v. Kerala, 2021).

## Slide 29
Gayatri Balasamy v. ISG Novasoft (2025)
Modifications must not rewrite the tribunal’s intent or re-evaluate evidence, preserving arbitration’s finality.
Section 34(4) allows remitting awards to tribunals for clarification or defect elimination (e.g., procedural errors), but courts can modify directly under Section 34 if remittance is unnecessary (e.g., severable errors).
Courts should prefer remittance to respect tribunal autonomy, per Kinnari Mullick v. Ghanshyam Das Damani (2018).
Severability and Partial Set-Aside:
Courts can partially set aside awards if the invalid part is distinct, avoiding full annulment (e.g., severing excessive damages, as in Hindustan Zinc v. Friends Coal, 2006).
This aligns with the New York Convention’s enforcement flexibility, ensuring valid portions survive.
Public Policy and Patent Illegality:
  Modifications must align with Section 34 grounds (e.g., patent illegality, public policy violations, post-2015 fraud/corruption).
  Unlike DMRC v. DAMEPL (2024), where an award was set aside for ignoring evidence, modifications here focus on surgical corrections, not wholesale reversals.

## Slide 30
Gayatri Balasamy v. ISG Novasoft (2025)
Dissent (Justice Viswanathan):
  Argued that Section 34 only allows setting aside, not modifying, to maintain minimal judicial intervention. Modifications risk courts acting as appellate bodies, undermining arbitration’s purpose.
  Suggested Article 142 or remittance under Section 34(4) as sufficient for justice, without expanding Section 34.
Outcome:
  The ruling clarified that courts can modify awards in limited cases, overturning M. Hakeem’s restrictive stance.
  The decision aims to balance equity (correcting clear errors) with arbitration’s finality, but critics warn it may invite protracted litigation by broadening judicial discretion.

## Slide 31
Relevance to Infrastructure Arbitration
Impact of Gayatri Balasamy on Infrastructure Cases:
  In TK Toll Road v. NHAI (2023) and DA Toll Road v. NHAI (2023), awards (Rs 1,204 crore each) were upheld without modification, as no severable errors existed. Gayatri Balasamy could allow courts to adjust specific award components (e.g., interest rates) in similar cases, avoiding full set-aside.
  In Afcons v. Ircon (2023), the upheld award for EOT and costs could face modification challenges if, e.g., computational errors were alleged, per Gayatri Balasamy’s framework.
  In DMRC v. DAMEPL (2024), the Supreme Court set aside a Rs 7,687 crore award via curative jurisdiction for patent illegality (ignoring CMRS evidence). Gayatri Balasamy might have allowed partial modification (e.g., adjusting damages) instead of annulment, preserving valid portions.

## Slide 32
Conclusion
Arbitration in Highway Projects: Arbitration serves as a crucial mechanism for resolving disputes in highway infrastructure projects, offering a structured and legally recognized process. Its role is pivotal in maintaining project timelines and ensuring that disagreements do not escalate into prolonged legal battles.
Balancing Speed and Fairness: While arbitration provides a faster alternative to traditional litigation, it's essential to balance this speed with the principles of fairness and justice. Ensuring that both parties have equal opportunities to present their cases upholds the integrity of the arbitration process.
Collaboration Among Stakeholders: Effective dispute resolution in highway projects requires collaboration between private entities, legal professionals, and policymakers. Such collaboration fosters an environment where disputes can be addressed proactively, minimizing disruptions to project progress.
Embracing Evolving Mechanisms: As the infrastructure sector evolves, so too must the mechanisms for dispute resolution, incorporating technological advancements and best practices. Staying abreast of these changes ensures that arbitration remains an effective tool for resolving complex infrastructure disputes.

## Slide 33
Thank You